## Project Plan
| PROJECT TYPE | 3D Enviroment |  |  |  |  | COMPANY NAME | [10 empty] | DEPI
| PROJECT TEAM MEMBERS | Nourelhoda Mohamed - Sarah Abdelwanees - Mohamed Hussein - Asmaa Eid |  |  |  |  | START DATE | [10 empty] | 2025-02-17
[7 empty] | DEADLINE | [10 empty] | 2025-04-11
Project Planning and Management
Project Name and Idea | A leaf Journey - is a mystical 3D journey through ancient Egypt, where an enchanted leaf drifts across iconic historical sites, unveiling their magic in a dreamlike atmosphere
Tools Used | 3Ds Max - Vray - Blender - Photoshop - After Effects - Premiere
[7 empty] | 2025-02-17 | [6 empty] | 2025-02-24 | [6 empty] | 2025-03-03 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07
 | time axis 2025-02-17 to 2025-04-13
NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | STATUS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
PHASE 1
Project Planning and Management
1 | Research & Refrences | Nourelhoda | 2025-02-15 | 2025-02-18 | 4 | Completed
2 | Storyboard | Mohamed, Sara, Asmaa | 2025-02-18 | 2025-02-19 | 2 | Completed
3 | Modeling | All Team | 2025-02-19 | 2025-03-05 | 15 | In Progess
4 | Camera & Lights | All Team | 2025-03-05 | 2025-03-14 | 10 | Not Started
5 | Animation | All Team | 2025-03-14 | 2025-03-23 | 10 | Not Started
6 | Composition | Sara, Mohamed | 2025-03-23 | 2025-03-31 | 9 | Not Started
PHASE 2
1 | Tasks Assignment
2 | Modeling: 1st scene "Gate" | Mohamed | 2025-02-20 | 2025-02-27 | 8 | In Progess
3 | Modeling: 2nd scene "Flooting City" |  | 2025-02-27 |  |  | Not Started
4 | Modeling: 3rd scene "Temple" | Nourelhoda | 2025-02-20 | 2025-02-27 | 8 | In Progess
5 | Modeling: 4th scene "Hall of the Temple" | Nourelhoda | 2025-02-20 | 2025-02-27 | 8 | In Progess
6 | Modeling: 5th scene "Bridge" | Asmaa | 2025-02-20 | 2025-02-27 | 8 | In Progess
7 | Modeling: 6th scene "Clock Tower" | Sarah | 2025-02-20 | 2025-02-27 | 8 | In Progess
8 | Modeling: 7th scene "Pyramids" |  | 2025-02-27 |  |  | Not Started
9 | Modeling: 8th scene "Paradise" |  | 2025-02-20 |  |  | Not Started
10 | Lights | All Team | 2025-03-05 |  |  | Not Started
11 | Camera | All Team | 2025-03-05 |  |  | Not Started
12 | Animation | All Team | 2025-03-14 |  |  | Not Started
13 | Composition | Sara, Mohamed | 2025-03-23 |  |  | Not Started
Formulas:
COMPANY NAME = [COMPANY NAME, row below]

## Requirements
Part | Links | Assigne
Literature Review | Link | Nourelhoda
Requirements Gatherings | https://docs.google.com/document/d/1yUndiaXP4T_0GiWdLpfblNscwDWd14TsN0y9bnE4vFA/edit?usp=sharing | Asmaa Eid Mohamed
System Analysis & Design | https://docs.google.com/document/d/1TsYlScJFbIABL28lcGw1Orx1Iw_xmK-KHtN854Ul-Qw/edit?usp=sharing | Asmaa Eid Mohamed